## Cover
AX2009 Roll out CIG-SAG
Project Sakura
GAP List (Version 1.2）
Jun. 13, 2019

## Interface
# | Module | File Name | In/Output | RequestNum | Description | Current Status | QA | Answer | Developer | Contacts
1 | Purchase | Completion list with SN | In | #6 | Upload the file into AX | Provided | We have already reviewed completion list with SN which will be uploaded by AX in future. But what's the difference between Part No. and Model in the file? AX might get multiple purchase lines by PO + ItemCode？Because purchase order may have multiple lines with the same itemcode. | Part No = Item Num, forget Model field. Multiple purchline with the same item code never exists. | Shaozhifang
2 | Purchase | Ftp.AWS(In) | In | #6 | Read date code from Aws cloud server by Itemcode and serialnum | Provided | Alternative solution: Can you ajust the way that AX system gets datecode? we suggest to add the datecode field into the file [Completion list with SN], and CM uploads the file with datecode together into AX rather than allow AX get it from Amazon AWS server? About Amazon AWS where date code is stored, will AWS address be switched to CIG cloud server? Or it is not going to be changed? How does CM factory import datecode into Amazon AWS? | Pending, SAG team will discuss internally, because currently EL side has datecode information, but FB does not have it. AX team provides 2 solutions: 1. Shpping list consists of datecode.(Prefered) 2. Input datecode in ax by SAG team after uploaded the file into AX. | Shaozhifang
3 | Purchase | Fail list | In | #6 |  | Not Provided | As you mentioned in last email, Only good FG and Sub-assembly are included in the shipping list. Defective products are not included in the shipping list. So Is there any defective product list file? If Yes, Can you provide to us? we also want to know the way SAG communicates with CM for this defective product list file? By Email, or other way? | CM sends detective list called status report to SAG by email. If both sides think they are not able to fix the detective good during rounds of investigation by R&D team and rework, CM will scrap it manually. SAG does not use rework workorder to fix the detective good, but CM charges to SAG for reparing fee monthly. Whether it is reasonable or not, it will be discussed by CIG_SH finance team. AX_Team waits to receive status report from SAG(Provided) | Shaozhifang
4 | Sales | Consumption PO file | In | #13 | Upload the file into AX | Provided | We understand AX automatically creates sales order based on this file.(no case of updating sales order) 1. PO NUMBER = sales order's customer PO Number? 2. which field of the file indicates Customer code? - is it set to the fixed value: Fabrinet? 3. which field of the file indicates inventsiteId? - is it set to the fixed value: Sagamihara? 4. what's purpose of SHIPMENT NUMBER field in the file? 5. what's purpose of LINE NUMBER field in the file? it seems AX does not need this field in the case of only creating sales order. 6. you mentioned the price's currency is always USD according to your email. but AX doesn't use the constant currency code - USD, normally currency code comes from each customer. So please be noted that the price CM provides in the text file should be in accordance with customer's currency code(not always USD). 7. Does Item Number field indicates customer item number or SAG item number? | Only one sales order is created for one comsumption PO file. 1.yes. 2.yes. 3.Wating for SAG to specify inventsiteid and warehouseid for this automatically created SO. 4.they do not use shipment number. 5.pending, they will discussed internally regading LINE NUMBER field. 6.Agreed by SAG. | Zhaoqiang
5 | Sales | Edata | Output | #26 | AX outputs Shipped products list with serial numbers into text file for customer reference | Provided | We have already reviewed Sample_Shipped_Serial_Number.txt file. It seems AX has sufficient information for that. But can you explain to us what each field means since fields in the file is not mapping with Table 1's fields definition in the Shipped_Products_Serial_number_20190602.pptx? | just based on table_1 | Shaozhifang
6 | Sales | Txt file for automatically posting packing slip | In | - | Upload the file into AX | Not Provided | As we understand, there should be a txt file uploaded by CM driving posting packingslip for sales order when CM is ready to ship out finish goods to our customer. But it has not been provided. We are not very sure if this file exists in your routine business with CM. If yes, Can you provide it to us? Can you provide the text file for EL side to manually posting SO packing slip? | Wait for the txt file: Currently FB auto post, EL manually post packing slip by the text file. They hope same method for both FB and EL. 2019/06/13: We have received it, but SN is not included in the file. What type is this file, Txt or csv? | Shaozhifang

## Business Report
# | Module | Report Name | In/Output | RequestNum | Description | Current Status | QA | Answer | Developer | Contacts
1 | Purchase | PO Document in Japanese and English | Output | #17 | when confirm purchase order, PO document is printed out with the language as same as the PO's language. | Not Provided | Alternative solution: we plan to implement English version report before go-live, and implement Japanese version after go-live. We have not received the report both English and Japanese version. | Agreed by SAG 2019/06/13: Provided and both version will be done before go-live. | Shaozhifang
2 | Sales | Outer Carton Label | Output | #11 | On the shipment of sales order, Outer carton label is printed and pasted outside each carton. | Provided | We have reviewed it breifly. There is no outer carton label in AX system, so it may be implemented by other system. But since we are not very sure the machanism about outer carton label function, Can you specifically explain it to us from the perspective of funtion? For example: Who prints it? CM or SAG members? when to print it? Before post packingslip or after post packingslip or at the same time of posting packingslip? where to print it? printed in SAG-SAP system currently? Whether one carton includes multiple SO's goods? How to calculate the weight? Please explain to us from the perspective of logic Is only one Item code included in the carton label? What is the encoding number for the barcode? Encode 39 or 128? If there are two datecode in one box, whether the outer carton label will be printed in two pages? | Currently picking list report is printed by CSR(operating team in future) and packing list report is printed by CM. CSR sends picking list report by email to CM and CM will pack goods according to the picking list. packing process for outputing packing report: CM inputs serial number and logistics information like box size, how many quantities per box etc.. and then print out packinglist, commercial invoice, outer carton label report. Most of sales reports need barcode, that's mandatory. There is only one item code and one SO number in outer carton label. Prefer A5 size for this report. AXTeam suggests to use sales packing slip registered form to output picking and packing reports rather than use standard picking action. AX allows users to manually input weight, boxnum, and so on about logistics information | Zhaoqiang
3 | Sales | Pickinglist | Output | #12 | Before shipment( post pickingslip), pickinglist is printed by SAG members and transferred to CM for guiding pack goods. | Provided | We have briefly reviewed the file - SalesOrderPickinglist(Standard)-編集済み.pdf. Whether pickingslip includes SN? You mentioned there is SN, but the file you sent does not include SN. | SN is not required in picking list report | Shaozhifang
4 | Sales | Delivery Note | Output | - | Picking list and Delivery note are sent to relevant people when products are picked for shipment | Provided | Alternative solution: AX does not have this output and Pickinglist report might covers most of information in this report, so we suggest put the necessary information of this report to Pickinglist report. According to QA survey document, we know that Delivery Note are sent to relevant people when products are picked for shipment, but Request document written by SAG does not include this request. Do you need this report? And are this report and picking list sent to CM for packing purpose? when to trigger the report print out? | Delivery note can be consolidated into picking list. | Shaozhifang
5 | Sales | Packingslip | Output | #12 | On the shipment(post packingslip), packingslip is printed by CM members. | Provided | We have received the report. But Is the SN needed in the line? | yes, SN is mandatory in packing slip. | Shaozhifang
6 | Sales | commercial invoice | Output | #12 | On the shipment(post packingslip), commercial invoice is printed by CM members. | Provided | We have briefly reviewed the file - SalesOrderInvoice(Standard)-編集済み.pdf. But I guess you might misunderstand which is commercial invoice in AX report sent to you last time. Please refer to the Screenshot-1 in the sheet of Screenshot and send to us again. | waiting for new file | Shaozhifang
7 | Sales | Outer Carton Label, Pickinglist, Packingslip, commercial invoice | Output | #11,#12 |  | Provided | In order to confirm our understanding is correct or not, Could you please specifically explain to us the relationship between these four reports of sales order from the following perspective. 1. When to trigger the output of each report? for example, before post packingslip, when post packingslip, after post packingslip. 2. What's the internal relationship for these four reports? 3. who trigger the output of each report. CM or SAG members? | Refer to answer of #2 | Shaozhifang
8 | Sales | SO Confirmation | Output | #12 | when confirm sales order, SO confirmation is printed. | Not Provided | Alternative solution: AX standard report will be used before go-live, we can customize it after go-live We have not received it. Please refer to the Screenshot-2 in the sheet of Screenshot and send to us again. | SAG don't care, please contact with rose team | Shaozhifang
9 | Sales | SO Standard Invoice | Output | #12 | when post invoice for sales order, SO Standard Invoice is printed. | Not Provided | Alternative solution: AX standard report will be used before go-live, we can customize it after go-live We have not received it. Please refer to the Screenshot-3 in the sheet of Screenshot and send to us again. | SAG don't care, please contact with rose team | Shaozhifang
10 | Sales | Sales Quotation | Output | #12 | when confirm sales quotation, Sales Quotation document is printed. | Not Provided | Alternative solution: AX standard report will be used before go-live, we can customize it after go-live We have not received it. Please refer to the Screenshot-4 in the sheet of Screenshot and send to us again. | SAG don't care, please contact with rose team | Shaozhifang

## Function
# | Module | Function Name | RequestNum | Description | QA | Answer | Developer | Contacts
1 | All | serial number management | #4 | Provide solution for Serial number management |  |  | Liuwuyun
2 | All | Inter-company solution | #14 | Provide inter-company solution |  |  | Dendi.Chen
3 | Inventory | Add a new field " hierarchy " on item master. | #1 | Set up Product Hierarchy field in item master for report purpose | Alternative solution: we can customize it after go-live | Agreed by SAG team | Shaozhifang
4 | Inventory | Add a new field " ECCN " on item master showing on commercial invoice. | #2 | Set up a field ECCN (Export Control Classification Number) for each item in item master |  |  | Shaozhifang
5 | Sales | Add a new field " Warranty Code " on customer master | #3 | Set up a field that can accommodate 'Warranty Code' in customer master |  |  | Shaozhifang
6 | Sales | Set up 'Pool' field in sales orders as mandatory field. | #8 | Set up 'Pool' field in sales orders as mandatory field. SAG users define category /pull-down e.g. Std order, CM custom order … |  |  | Shaozhifang
7 | Sales | Add a new field " Ship method " on customer and sales order, used to show on the reports. | #9 | Set up a field that can accommodate a note as for shipment so as to be printed on Picking List and Packing Slip. |  |  | Shaozhifang
8 | Sales | Auto posting packingslip for SO after CM FG shipping list uploaded | - | Auto posting packingslip for SO after CM FG shipping list uploaded | Alternative solution: Before go-live, AX system will allow CM factory to manually maintain logistics information like net-weight, gross-weight, BOX number etc for reports related with SO after uploaded shipping list for SO and manually post SO. we can make it automatically after go-live. | Top priority after go-live | Shaozhifang
9 | Sales | Auto creating SO and posting packingslip for that after CM RM demand text file uploaded | #13 | Auto creating SO and posting packingslip for that after CM RM demand text file uploaded | Alternative solution: Before go-live, AX system will automatically create sales order based on the CM RM demand text file, but end-user needs manually post packingslip for the SO. we can make implement auto-posting packingslip functionality after go-live. | Agreed by SAG team | Zhaoqiang
10 | Sales | Only for inter-company sales order,there might be some issues for Reports output from CM factory about where fields value comes from, needs to be futher discussed. | #11,#12 | Only for inter-company sales order,there might be some issues for Reports output from CM factory about where fields value comes from, needs to be futher discussed. |  |  | Zhaoqiang
11 | Sales | Replace picking function with Sales packing slip registered form | #12 | Replace picking function with Sales packing slip registered form and maintain information for reports. |  | Replace picking function with Sales packing slip registered form | Zhaoqiang
12 | Production | Auto posting PO and WO after completion list uploaded by CM | #6 | Auto post packing slip for outsourcing fee FG PO and update reported as finish for the production order after CM-FB FG completion list uploaded |  |  | Liuwuyun
13 | Purchase | Auto posting packingslip for PO after CM-FB sub-FG and CM-EL FG shipping list uploaded | #6 | Auto posting packingslip for PO after CM-FB sub-FG and CM-EL FG shipping list uploaded |  |  | Liuwuyun

## Screenshot
Screenshot-1
Original file: SalesOrderCommercialInvoice14876074.xlsx in AxReport.zip sent to you last time
Screenshot-2
Original file: SalesOrderConfirmation14875123.xlsx in AxReport.zip sent to you last time
Screenshot-3
Original file: SalesOrderInvoice(Standard).pdf in AxReport.zip sent to you last time
Screenshot-4
I am going to send this AX standard report named as Quotation15638886.xlsx for your reference in a seperate email.

## listRef
Purchase | Provided | In | Zhaoqiang | Interface | 100%
Sales | Not Provided | Output | Liuwuyun | Business Report | 0%
Production |  |  | Shaozhifang | Function | 50%
Inventory |  |  | Dendi.Chen
All